## Cover
TEST REPORT DOCUMENT
Project Name | Japanese Certification Learning and Exam Preparation Application |  |  | Creator | quyndse171895@fpt.edu.vn
Project Code | SU25SE037 |  |  | Issue Date | 2025-08-25
Document Code | SU25SE037_Test Report_WebUser_v1.0 |  |  | Version | 1
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2025-08-25 | 1.0 | All | A | Add new | N/A

## Test Cases
TEST CASE LIST
Project Name |  | Japanese Certification Learning and Exam Preparation Application
Project Code |  | SU25SE037
Test Environment Setup Description |  | 1. JCertPre API Server 2. Postgre SQL Server 3. Google Chrome
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Renter Register | Authentication
2 | Renter Login | Authentication
3 | Renter Forgot password | Authentication
4 | Renter Edit profile | Authentication
5 | Renter Change password | Authentication
6 | Renter View list of houses | Homepage Feature
7 | Renter Seach house | Homepage Feature
8 | Renter View houses from Map | Homepage Feature
9 | Renter View house detail | Homepage Feature
10 | Rener Reserve a house | Reserve Feature
11 | Renter View list of reservation | Reserve Feature
12 | Renter View list of leases | Lease Feature
13 | Renter Cancel lease | Lease Feature
14 | Renter View list of request | Extra Service Feature
15 | Renter Cancel request | Extra Service Feature
16 | Send contact requrest | Contact Us Feature
17 | Report issue | Contact Us Feature
18 | Renter View notification list | Notification Feature

## Test Statistics
TEST STATISTICS
Project Name | Japanese Certification Learning and Exam Preparation Application |  | Creator |  | quyndse171895@fpt.edu.vn
Project Code | SU25SE037 |  | Reviewer/Approver
Document Code | SU25SE037_Test Report_WebUser_v1.0 |  | Issue Date |  | 2025-08-25
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Authentication Feature | 34 | 0 | 0 | 0 | 34
2 | House Feature | 40 | 0 | 0 | 0 | 40
3 | Reserve Feature | 14 | 0 | 0 | 0 | 14
4 | Lease Feature | 11 | 0 | 0 | 0 | 11
5 | Extra Service Feature | 7 | 0 | 0 | 0 | 7
6 | Contact Us Feature | 8 | 0 | 0 | 0 | 8
7 | Notification Feature | 6 | 0 | 0 | 0 | 6
| Sub total | 120 | 0 | 0 | 0 | 120
| Test case coverage |  | 100 | %
| Test successful coverage |  | 100 | %

## Authentication
Feature | Authentication Feature | [13 empty] | Passed
Test requirement | To ensure that feature of authentication works properly | [13 empty] | Failed
Number of TCs | 34 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 34 | 0 | 0 | 0
Round 2 | 34 | 0 | 0 | 0
Round 3 | 34 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter Register
[Authentication Feature-1] | Verify register a registered account | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input a registered Email 6. Password, Repeat Password. | "Email already exists" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-2] | Verify register with empty email | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input " " in email box | "Email is required" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-3] | Verify register with empty password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input " " in password box | "Password is required" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-4] | Verify register with empty repeat password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input " " in repeat password box | "Repeat password is required" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-5] | Verify register with short password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input "a" in password box | "Password must be at least 8 characters" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-6] | Verify register without any digit character | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input "aaaaaaaa" in password box | "Password must contain at least one digit" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-7] | Verify register without any uppercase character | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input "aaaaaaaa1" in password box | "Password must contain at least one uppercase character" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-8] | Verify register without any special character | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input "aaaaaaaa1A" in password box | "Password must contain at least one special character" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-9] | Verify register with invalid repeat password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input "Ab123456!" in password box 6. Input "Ab123456" in repeat password box | "Passwords must match" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-10] | Verify register a new account | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Register here 5. Input valid Email, Password, Repeat Password. | App display Verification screen and OTP should send to email. | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-11] | Verify invalid OTP code | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Forgot password 5. Input email 6. Click Reset password | "Invalid OTP code" is displayed | Account must be registered in the system. | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-12] | Verify OTP code | 1. At the Verfication screen 2. Get the OTP from email 3. Input the OTP | Login successfully, and app display "User" tab with login profile. | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Login
[Authentication Feature-13] | Verify login with input empty email | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input empty email | "Email is required" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-14] | Verify login with input empty password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input empty password | "Password is required" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-15] | Verify login with invalid email or password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input valid email and invalid password | "Email or password is incorrect" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-16] | Verify login with email and password but wrong role | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input email and password for role Staff | "The account role is incorrent" is displayed | Account must already be registered as Staff/Manager/Admin role | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-17] | Verify login after Admin suspended | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input Email and Password 5. Click "Sign in" | "Your account has been suspended" is displayed | Account must already be registered as Renter role | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-18] | Verify login with Google account | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Google button 5. Choose an account | Login successfully, and app display "User" tab with login profile. | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-19] | Verify login with email and password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Input Email and Password 5. Click "Sign in" | Login successfully, and app display "User" tab with login profile. | Account must already be registered as Renter role | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Forgot password
[Authentication Feature-20] | Verify forgot password with unregistered email | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Forgot password 5. Input an unregisterd email | "Email is unregistered" is displayed | Account must be registered in the system. | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-21] | Verify forgot password with invalid email | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Forgot password 5. Input email 6. Click Reset password | "Email is invalid" is displayed | Account must be registered in the system. | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-22] | Verify invalid OTP code | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Forgot password 5. Input email 6. Click Reset password | "Invalid OTP code" is displayed | Account must be registered in the system. | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-23] | Verify UI of forgot password | 1. Open webapp 2. Navigates to "Join Us" tab 3. "Sign in" screen appears 4. Click on Forgot password 5. Input email 6. Click Reset password | App display verification screen and OTP send to email. | Account must be registered in the system. | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-24] | Verify reset password | 1. Get OTP from email 2. At verification page 3. Input Password, Repeat Password and OTP | Login successfully, and app display "User" tab with login profile. | Account must be registered in the system and received OTP code from email | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Edit profile
[Authentication Feature-25] | Verify UI of profile screen | 1. Open webapp 2. Navigates "Profile" under profile icon | Should be shown the profile screen. | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-26] | Verify UI of edit profile | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Input new information 5. Tap "Edit" button | Should be shown the edit profile screen. | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-27] | Verify upload profile picture | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Upload new profile picture | Should be shown the edit profile screen with new profile picture | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-28] | Verify update phone number | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Input new phone number | Should be shown the edit profile screen with new phone number | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-29] | Verify update last name | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Input new last name | Should be shown the edit profile screen with new last name | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-30] | Verify update country | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Input new country | Should be shown the edit profile screen with new country | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-31] | Verify update first name | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Input new first name | Should be shown the edit profile screen with new first name | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Change password
[Authentication Feature-32] | Verify change password with incorrect current password | 1. In “Change password” screen 2. Input incorrect current password, new password, and repeat new password. 3. Tap “Change password” button | "Current password is incorrect" is displayed | Renter logged in succesfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-33] | Verify UI of change password screen | 1. Open webapp 2. Navigates "Profile" under profile icon 3. Click "Edit Profile" option 4. Tap on “Change password” option | Should display “Change password” screen | Renter logged in succesfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Authentication Feature-34] | Verify change password | 1. In “Change password” screen 2. Input current password, new password, and repeat new password. 3. Tap “Change password” button | Should be updated password successfully | Renter logged in succesfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## House Feature
Feature | House Feature | [13 empty] | Passed
Test requirement | To ensure that feature of house works properly | [13 empty] | Failed
Number of TCs | 40 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 40 | 0 | 0 | 0
Round 2 | 40 | 0 | 0 | 0
Round 3 | 40 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter View list of houses
[House Feature-1] | Verify house image | 1.Open webapp 2.Navigate to House screen | List of available house, minor details and house picture is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-2] | Verify house carousel image | 1.Open webapp 2.Navigate to House screen 3. Swipe house picture | House picture changes to a different picture | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-3] | Verify view House List | 1.Open webapp 2.Navigate to House screen | Should be shown the Search screen, included: - Search house box. - List of available houses. - Map button | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter View list of houses
[House Feature-4] | Verify empty house name | 1. Open webapp 2. Navigate to House screen 3. Click on search bar 4. Input " " in name box | List of all available houses is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-5] | Verify unique house name | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "Abcdefg" in name box | "No houses match your search" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-6] | Verify valid house name | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "Ha Do" in name box | List of all available houses that fits search results is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-7] | Verify location with province first | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Tap "Select province" box | List of all provinces is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-8] | Verify location with district first | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Tap "Select province first" box | Only "Select province first" option is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-9] | Verify location with ward first | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Tap "Select district first" box | Only "Select district first" option is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-10] | Verify location with province, district, ward respectively | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose "Ho Chi Minh City" in Province box 5. Choose "District 7" in District box 6. Choose "Tay Quy Ward" in Ward box 7. Tap "Apply" button | List of all available houses that fits search results is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-11] | Verify min price | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Drag min price slider | Minimum price amount changed based on slider position | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-12] | Verify max price | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Drag max price slider | Maximum price amount changed based on slider position | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-13] | Verify drag min price over max price | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Drag min price slider | Max amount of minimum price is equal to maximum price | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-14] | Verify drag max price over min price | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Drag min price slider | Min amount of maximum price is equal to minimum price | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-15] | Verify negative value for minimum size | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "-100" in minimum size box | 100 is displayed in minimum size box | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-16] | Verify negative value for maximum size | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "-100" in maximum size box | 100 is displayed in maximum size box | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-17] | Verify min size is bigger than max size | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "100" in maximum size box 5. Input "99" in minimum size box | "Max area must be greater than 100" is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-18] | Verify negative amount bedroom | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "-1" in bedroom box | 100 is displayed in bedroom box | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-19] | Verify negative amount bathroom | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "-1" in bathroom box | 100 is displayed in bathroom box | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-20] | Verify valid bedroom | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "2" in bedroom box 5. Tap "Apply" button | List of all available houses that fits search results is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-21] | Verify valid bathroom | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "2" in bathroom box 5. Tap "Apply" button | List of all available houses that fits search results is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-22] | Verify categories with one option choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose one option in Categories | Checkbox of the option is chose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-23] | Verify categories with multiple option choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose multiple options in Categories | Checkbox of multiple options is chose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-24] | Verify categories with double tap an option | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Double tap one option in Categories | Checkbox of the option is unchose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-25] | Verify amenities with one option choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose one option in Amenities | Checkbox of the option is chose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-26] | Verify amenities with multiple option choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose multiple options in Amenities | Checkbox of multiple options is chose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-27] | Verify amenities with double click an option | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Double tap one option in Amenities | Checkbox of the option is unchose | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-28] | Verify clear option | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Input "Ha Do" in name box | Clear all the input in search page | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-29] | Verify house search | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar | Should be shown the Advance Filter screen, included house filter options (name, location, price, size, room, categories, amenities) | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-30] | Verify search feature | 1. Open webapp 2. Navigate to House screen 3. Tap on search bar 4. Choose desired house filter options 5. Tap “Apply” button | Should displayed list of available house that have all the options. | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter View houses from Map
[House Feature-31] | Verify Map | 1. Open webapp 2. Navigate to House screen 3. Tap on "Map" button | Should displayed Google Maps with all the house that are in the list | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-32] | Verify view house from Map | 1. Open webapp 2. Navigate to House screen 3. Tap on "Map" button 4. Tap on a house | Should displayed a house | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter View house detail
[House Feature-33] | Verify house carousel image | 1. Open webapp 2. Navigate to House screen 3. Tap on a house 4. Swipe house picture | House picture changes to a different picture | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-34] | Verify reviews with "x reviews" choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on a house 4. Tap "x reviews" next to rating | List of reviews is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-35] | Verify reviews with show all reviews choosed | 1. Open webapp 2. Navigate to House screen 3. Tap on a house 4. Tap "Show all x reviews" | List of reviews is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-36] | Verify show all amenities | 1. Open webapp 2. Navigate to House screen 3. Tap on a house 4. Tap "Show all x amenities" | List of amenities is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-37] | Verify show all utilities | 1. Open webapp 2. Navigate to House screen 3. Tap on a house 4. Tap "Show all x utilities" | List of utilities is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-38] | Verify location on Map | 1. Open webapp 2. Navigate to House screen 3. Tap on a house | House location is displayed on Google Map | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-39] | Verify access House Details from Map | 1. Open webapp 2. Navigate to "Browse more properties" option in House 4. Tap on "Map" button 5. Tap on a house 6. Tap on house picture | Should displayed house details | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[House Feature-40] | View House Details | 1. Open webapp 2. Navigate to House screen 3. Tap on a house | Should displayed the house details | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## Reserve Feature
Feature | Reserve Feature | [13 empty] | Passed
Test requirement | To ensure that feature of reserve works properly | [13 empty] | Failed
Number of TCs | 14 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 14 | 0 | 0 | 0
Round 2 | 14 | 0 | 0 | 0
Round 3 | 14 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter Reserve a house
[Reserve Feature-1] | Verify Reserve a house | 1. In House Details screen 2. Tap “Check out” button | Reservation page is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-2] | Verify UI of VNPay Payment page | 1. In reservation page 2. Enter expected move in date and duration of rental 3. Choose a payment method | Payment page is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-3] | Verify UI of reservation page | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Press for better price" option | Reservation page with expected move in date box and total months box is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-4] | Verify UI of checkout page | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Check out" button | Checkout page is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-5] | Verify checkout page with options choosed | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Choose move in date and total months in Reservation page 5. Tap "Check out" button | Checkout page with choosed move in date and total months is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-6] | Verify checkout page without options choosed | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Check out" button | Checkout page without choosed move date and default total months is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-7] | Verify choosing payment method | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Check out" button 5. Choose VNPay payment method | VNPay option is choosed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-8] | Verify expected move in date | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Check out" button 5. Choose "3/30/2024" in expected move in date box | 30/3/2024 is displayed in expected move in date box | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-9] | Verify total months | 1.Open webapp 2.Navigate to House screen 3. Tap on a house 4. Tap "Check out" button 5. Choose "12 months" in total months box | 12 months is displayed in total months box | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-10] | Verify pricing policy | 1. Open webapp 2. Navigates to House screen 3. Tap on a house 4. Tap 4 months, 6 months, adn 12 months respectively in total months box | Pricing policy is changed for each total months | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-11] | Verify payment confirmation | 1. In Payment page 2. Complete payment process | Should displayed reservation confirmation prompt | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter View list of reservation
[Reserve Feature-13] | Verify filter list of reservation | 1. Open webapp 2. Navigates to User tab 3. Tap on “View all reservations” option 4. Tap "Payment pending" options | List of reservation with "Payment pending" status is displayed | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-14] | Verify view list of reservation | 1. Open webapp 2. Navigates to User tab 3. Tap on “View all reservations” option | Should displayed list of reservation | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Reserve Feature-15] | Verify reservation details | 1. Open webapp 2. Navigates to User tab 3. Tap on “View all reservations” option 4. Tap on a reservation | Should displayed reservation details | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## Lease Feature
Feature | Lease Feature | [13 empty] | Passed
Test requirement | To ensure that feature of lease works properly | [13 empty] | Failed
Number of TCs | 11 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 11 | 0 | 0 | 0
Round 2 | 11 | 0 | 0 | 0
Round 3 | 11 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter View list of leases
[Lease Feature-1] | Verify view files | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on a lease 5. Tap "Show x contracts" option | List of contract and view button is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-2] | Verify access house detail from lease details | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on a lease 5. Tap on house picture | House details page is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-3] | Verify filter lease | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on “View all reservations” option 5. Tap "Active" options | List of reservation with "Active" status is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-4] | Verify leases UI | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab | List of lease is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Cancel lease
[Lease Feature-5] | Verify cancellation request UI | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap an "Active" reservation 5. Tap "Request cancellation" button | Cancellation Request page is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-6] | Verify cancellation form cancellation type | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap an "Active" reservation 5. Tap "Request cancellation" button 6. Tap "Cancellation Type" option | A dropdown list of cancellation type is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-7] | Verify cancellation form with empty title | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap an "Active" reservation 5. Tap "Request cancellation" button | "Title is required" is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-8] | Verify cancellation form with empty reasons | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap an "Active" reservation 5. Tap "Request cancellation" button | "Reason is required" is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-9] | Verify leases details | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on a lease | Should be all detail about the lease | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-10] | Verify UI of leases cancellation request | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on a lease 5. Tap on "Request cancellation" button | Should be shown Cancellation Request screen | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Lease Feature-11] | Verify leases cancellation request successfully | 1. Open webapp 2. Navigate to "Management" tab under Profile Icon 3. Navigate to "Contract" tab 4. Tap on a lease 5. Tap on "Request cancellation" button 6. Input Title, Reason and Cancellation Type 7. Submit request | "Your cancellation request has been send successfully" is displayed | Renter logged in successfully Renter have at least one active leases | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## Extra Service Feature
Feature | Extra Service Feature | [13 empty] | Passed
Test requirement | To ensure that feature of extra service works properly | [13 empty] | Failed
Number of TCs | 7 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 7 | 0 | 0 | 0
Round 2 | 7 | 0 | 0 | 0
Round 3 | 7 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter View list of request
[Extra Service Feature-1] | Verify request extra service successfully | 1. Open webapp 2. Navigates to "Our Service" tab in "Support Us" navbar 3. Click "Request" 4. Choose a lease 5. Choose "Water bill payment service" option 6. Input title and reason 7. Submit form | "Your extra service request has been sent successfully" is displayed | Renter logged in successfully Renter have at least one active lease Renter have not requested the same service beforehand | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Extra Service Feature-2] | Verify filter extra service request | 1. Open webapp 2. Navigates to "Managerment" tab in "Profile" navbar 3. Click "Extra Services" tab 4. Choose a status | List of reservation with "In Progress" status is displayed | Renter logged in successfully Renter have at least one request | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Extra Service Feature-3] | Verify request same service twice | 1. Open webapp 2. Navigates to "Our Service" tab in "Support Us" navbar 3. Click "Request" 4. Choose a lease 5. Choose "Water bill payment service" option 6. Input title and reason 7. Submit form | "This requested service is in progress" is displayed | Renter logged in successfully Renter have at least one active lease Renter have request Water bill payment service beforehand | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Extra Service Feature-4] | Verify UI of extra service request | 1. Open webapp 2. Navigates to "Managerment" tab in "Profile" navbar 3. Click "Extra Services" tab | Should displayed list of request | Renter logged in successfully Renter have at least one active lease Renter have at least one request | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter Cancel request
[Extra Service Feature-5] | Verify request details | 1. Open webapp 2. Navigates to "Managerment" tab in "Profile" navbar 3. Click "Extra Services" tab | Should be all detail about the request | Renter logged in successfully Renter have at least one active lease | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Extra Service Feature-6] | Verify UI of request cancellation request | 1. Open webapp 2. Navigates to "Managerment" tab in "Profile" navbar 3. Click "Extra Services" tab 4. Click an "Under Review" request 5. Click "Request Cancel" button | Cancellation Request screen is displayed | Renter logged in successfully Renter have at least one active lease | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Extra Service Feature-7] | Verify successfully cancel request | 1. Open webapp 2. Navigates to "Managerment" tab in "Profile" navbar 3. Click "Extra Services" tab 4. Click an "Under Review" request 5. Click "Request Cancel" button 6 Click "Yes" on confirmation prompt | Cancellation request is sucessfully canceled | Renter logged in successfully Renter have at least one "Under Review" request | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## Contact Us Feature
Feature | Contact Us Feature | [13 empty] | Passed
Test requirement | To ensure that feature of contact us works properly | [13 empty] | Failed
Number of TCs | 8 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 8 | 0 | 0 | 0
Round 2 | 8 | 0 | 0 | 0
Round 3 | 8 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Renter report issue
[Contact Us Feature-1] | Verify UI of living issue request screen | 1. Open webapp 2. Navigates to "Management" tab in "Profile" 3. Choose a lease in "Contract" tab 4. Click "Report living issue" | Living issue request screen is displayed | Renter logged in successfully Renter have at least one active lease | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-2] | Verify UI of invoice issue request screen | 1. Open webapp 2. Navigates to "Management" tab in "Profile" 3. Choose an invoice in "Rental Fees" tab 4. Click "Report invoice issue" | Invoice issue request screen is displayed | Renter logged in successfully Renter have at least one pending invoice | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-3] | Verify successfully report living issue | 1. Open webapp 2. Navigates to "Management" tab in "Profile" 3. Choose a lease in "Contract" tab 4. Click "Report living issue" 5. Fill in message and upload picture. | Living issue is succesfully reported | Renter logged in successfully Renter have at least one active lease | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-4] | Verify successfully report invoice issue | 1. Open webapp 2. Navigates to "Management" tab in "Profile" 3. Choose an invoice in "Rental Fees" tab 4. Click "Report invoice issue" 5. Fill in message and upload picture. | Invoice issue is succesfully reported | Renter logged in successfully Renter have at least one pending invoice | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-5] | Verify view list of issue | 1. Open webapp 2. Navigates to "Management" tab in "Profile" 3. Click "Issue" tab | List of issues is displayed | Renter logged in successfully Renter have at least one issue report | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
Renter send contact request
[Contact Us Feature-6] | Verify UI of contact request | 1. Open webapp 2. Navigates to "Contact Us" tab in "Support" tab | Contract request screen is displayed | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-7] | Verify successfully send Homeowner Lease Inquiry contact request | 1. Open webapp 2. Navigates to "Contact Us" tab in "Support" tab 3. Choose "Homeowner Lease Inquiry" category 4. Fill in message and submit form | Contact request is sent successfully | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Contact Us Feature-8] | Verify successfully send Other contact request | 1. Open webapp 2. Navigates to "Contact Us" tab in "Support" tab 3. Choose "Other" category 4. Fill in message and submit form | Contact request is sent successfully | N/A | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn

## Notification Feature
Feature | Notification Feature | [13 empty] | Passed
Test requirement | To ensure that feature of notification works properly | [13 empty] | Failed
Number of TCs | 6 | [13 empty] | Pending
Testing Round | Passed | Failed | Pending | N/A | [10 empty] | N/A
Round 1 | 6 | 0 | 0 | 0
Round 2 | 6 | 0 | 0 | 0
Round 3 | 6 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View notification list
[Notification Feature-1] | Verify notification icon | 1. Open webapp | Should be shown the notification icon with correct number of unread notifications | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Notification Feature-2] | Verify UI of list of notification | 1. Open webapp 2. Navigates to “Notification” icon | Should be shown the List of notifications | Renter logged in successfully | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Notification Feature-3] | Verify access lease cancellation request from notification | 1. Open webapp 2. Navigates to “Notification” icon 3. Tap on lease cancellation request | Cancellation Request page is displayed | Renter logged in successfully Renter have requested lease cancellation beforehand | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Notification Feature-4] | Verify access invoice detail from notification | 1. Open webapp 2. Navigates to “Notification” icon 3. Tap on invoice notification | Invoice detail page is displayed | Renter logged in successfully Renter have an "Active" lease | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Notification Feature-5] | Verify access issue report from notification | 1. Open webapp 2. Navigates to “Notification” icon 3. Tap on issue report notification | Issue report page is displayed | Renter logged in successfully Renter have an "Active" lease Renter sent an issue report Staff/Manager has processed the issue report | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn
[Notification Feature-6] | Veirfy access extra service request from notifcation | 1. Open webapp 2. Navigates to “Notification” icon 3. Tap on extra service request notification | Extra service request page is displayed | Renter logged in successfully Renter have an "Active" lease Renter sent an extra service request Staff/Manager has processed the extra service request | Passed | 2024-03-30 | minhlnn | Passed | 2024-04-02 | minhlnn | Passed | 2024-04-04 | minhlnn